## PLAN
Due to legal reasons this document do not contain personal data | Communication plan
PARTNER'S NAME | ACTION | DESCRIPTION OF EVENT/INIZIATIVE | TOOLS SELECTED | DEADLINE | STAKEHOLDERS INVOLVED | STATUS | NOTES
ENEA | D1 | Press release | ENEAinform@ | 2017-12-14 | national and international media, companies, public administrations, local bodies, associations and institutions | DONE
Camst | D1 | Press release and social media diffution (facebook, twetter, linkedin) |  | 2017-12-19 | civil society
CAM | D1 | Press release |  | 2018-01-10 | civil society
Assofond | D1 | Caef director | communication material distributed | 2018-01-15 | european associates | DONE
AGRICA | D1 | Press release |  | 2018-02-10 | civil society
ENEA | D1 | Lesson at schools | frontal didactics | 2018-02-28 | high school students | DONE, SEE PHOTOS
CAM | D1 | Public event in Mantua to introduce EFFIGE to local companies |  | 2018-03-13 | companies and company unions
Assofond | D1 | technical article | specialized magazine, Assofond network | 2018-04-30 | companies, institutions, others | DONE
AGRICA | D1 | Public event in Benevento to introduce EFFIGE to local companies |  | 2018-05-30 | companies and company unions
Assofond | D1 | Genaral meeting | communication material distributed | 2018-06-20 | associates, all stakeholders, specialized press | DONE
Assofond | D1 | Bocconi University Sustainability Management Barometer | speech by President Ariotti | 2018-07-11 | stakeholders, specialized press, students, reserarchers | DONE
Assofond | D1 | Bocconi University Sustainability Management Barometer | press release | 2018-07-11 | national, local and specialized press | DONE
Assofond | D1 | News about PEF Internalization | Assofond News | 2018-08-02 | associates | DONE
CAM | D1 | Public workshop at Fiera Millenaria di Gonzaga |  | 2018-09-09 | companies, institutions, others
Assofond | D1 | Political and Economic congress | communication material distributed | 2018-10-18 | associates, stakeholders | DONE
Assofond | D1 | technical article | specialized magazine, Assofond network | 2018-10-30 | companies, institutions, others | DONE
Assofond | D1 | publich speech together with SSSUP | speech by GM Squaratti | 2018-11-09 | stakeholders, specialized press, students, reserarchers | DONE
Assofond | D1 | Ecomondo | press release | 2018-11-09 | national, local and specialized press | DONE
AGRICA JOINT WITH SSSUP | D1 | Public workshop at ECOMONDO |  | 2018-11-10 | companies, institutions, others
Assofond | D1 | Technical congress | communication material distributed | 2018-11-15 | associates, all stakeholders, specialized press | DONE
Assofond | D1 | Caef HPDC Meeting | communication material distributed | 2018-11-15 | european foundry associations | DONE
Assofond | D1 | Technical congress | presentation by Andrea Bianchi | 2018-11-15 | associates, stakeholders, local and specialized press | DONE
Assofond | D1 | Technical congress | interview by President Ariotti | 2018-11-15 | local press | DONE
Assofond | D1 | Amafond convention | communication material distributed | 2018-11-30 | companies, institutions, others | DONE
FLAE | D1 | Rapporto GreenItaly 2018 | Publication of the Green Italy Report 2018 containing references to the Effige project | 2018-11-30 | national and international media, companies, public administrations, local bodies, associations and institutions | DONE, document
FLAE | D1 | Ecomondo | Made Green in Italy Conference / EFFIGE at Ecomondo - FLA experience presentation | 2018-11-30 | national and international media, companies, public administrations, local bodies, associations and institutions | DONE
ENEA | D1 | Ecomondo | communication material distributed at ENEA stand | 2018-11-30 | companies, institutions, others | DONE, SEE PHOTOS
ENEA | D2 | Networking | Meeting | 2018-11-30 | TECHNICAL MEETING WITH RESEARCHERS INVOLVED IN PEFMED AND LIFE TTGG 16/11/2018 | done, see minutes
Assofond | D1 | Assofond cast iron meeting | communication material distributed | 2018-12-12 | associates | DONE
ENEA | D1 | News on EFFIGE | Rete Italiana LCA Newsletter | 2018-12-31 | Companies, academics, researchers | DONE
AGRICA | D1 | article in Italian |  | 2018-12-31 | companies, institutions, others
FLAE | D1 | press release on the Officelayout | publication of the dedicated news item in the interior design magazine / Officelayout office | 2019-01-31 | National and international media, sector companies, associations | DONE, paper submitted
FLAE | D1 | FLA site web, EFFIGE news | Dissemination action of the EFFIGE project with the publication of dedicated news on the FederlegnoArredo website & on the Assoufficio showcase | 2019-01-31 | Sector companies, associations | DONE, FLA site
Camst | D1 | Francesco Malaguti (Camst Chairman) presence at FAO |  | 2019-02-01 | companies, institutions, others
FLAE | D1 | Bocconi Observatory Meeting No Greenwashing | Bocconi Observatory Meeting "No Greenwashing" which discussed the progress of the EFFIGE project | 2019-02-28 | Companies, researchers, associations, national media | DONE (Photos)
FLAE | D1 | Stand at Mado Expo fair | Dissemination action of the EFFIGE project through a stand dedicated to the national MADE EXPO fair | 2019-03-31 | Companies, associations, national and international media, public administrations, local bodies, institutions | DONE (Photos, Brochure)
FLAE | D1 | EFFIGE dissemination at Salone del Mobile 2019 | Dissemination action with brochure at Salone del Mobile 2019 | 9-14/04/2019 | Companies, associations, national and international media, public administrations, local bodies, institutions | Done (brochure)
CAM | D1 | article in Italian |  | 2019-04-11 | companies, institutions, others
Assofond | D1 | AIB (Associazione Industriale Bresciana) Metallurgy Industry Meeting | presentation by President Ariotti | 2019-05-07 | entepreneurs in the metallurgy sector | DONE
Camst | D1 | Simone Gozzi Amsterdam |  | 13-14/5/2019 | companies, institutions, others
ENEA | D2 | Networking | Final Conference of PEFMED (pefmed.interreg-med.eu) | 2019-05-27 | Companies, academics, researchers | done, see photos
CAM | D1 | public workshop at CAM annual event - Sustinente |  | 2019-05-27 | companies, institutions, others
Assofond | D1 | Techinical article | specialized magazine, Assofond network | 2019-05-30 | companies, institutions, others | DONE
ENEA | D2 | Networking | Meeting with Italian regions and Ministry of Environment 'Cabina di regia Nazionale sulla valutazione del ciclo di vita del prodotto (LCA)' | 2019-05-30 | public administration | done
FLAE | D1 | EFFIGE dissemination at FLA's Environment Commission | Dissemination activities of the EFFIGE project during the Environment Commission of 3 June 2019 carried out by the Project Development Office | 2019-06-03 | Sector companies | Done (Photos, document)
ENEA | D1 | Oral presentation | Convegno Rete Italiana LCA | 2019-06-13 | Companies, academics, researchers | done, see slides and photos
ENEA | D1 | Article | Proceedings Conference Rete Italiana LCA | 2019-06-13 | Companies, academics, researchers | done
Camst | D2 | Corporate brochure Camst |  | 2019-06-21 | companies, institutions, others
Assofond | D1 | CAEF Non ferrous Foundries meeting in Dusseldorf | presentation by Andrea Bianchi | 2019-06-27 | 20 people, companies | DONE
ENEA | D1 | Oral presentation | Meeting (CReIAMO PA days) | 2019-07-03 | public administration | DONE, SEE PHOTOS
Assofond | D1 | Assofond general Assembly | project mentioned by president Ariotti | 2019-07-05 | 243 people, foundries and stakholders | DONE
Camst | D2 | article in Italian on Food HUB magazine (www.foodhubmagazine.com) |  | 2019-09-05 | companies, institutions, researchers, civil society
Camst | D1 | Presence at SANA 2019 |  | 2019-09-09 | companies, institutions, others
Camst | D1 | Presence at "Good is green" |  | 2019-09-09 | companies, institutions, others
Assofond | D1 | HPDC School final event | presentation by Andrea Bianchi | 2019-10-15 | 45 people, foundries and stakholders | DONE
Camst | D1 | Public workshop/Presence at ECOMONDO |  | 5-8/11/ 2019 | companies, institutions, others
Assofond | D1 | Ecomondo | communication material distributed | 05-08/11/2019 | companies, institutions, others | DONE
Assofond | D1 | Ecomondo | press releases | 2019-11-08 | national, local and specialized press | DONE
Assofond | D1 | Ecomondo - mid-term conference | press releases | 2019-11-08 | 100 people companies, institutions, others | DONE
Assofond | D1 | High School lesson at ITIS Marzoli | presentation by Andrea Bianchi | 2019-11-12 | 90 people, students | DONE
Camst | D1 | Public event "Parole che creano futuro" |  | 2019-11-15 | companies, institutions, others
Assofond | D1 | Event "Green new deal, risk or opportunity"? | presentation by Andrea Bianchi | 2019-11-24 | 24 people, assofond member companies | DONE
ENEA | D1 | Ecomondo | communication material distributed at ENEA stand | 2019-11-30 | companies, institutions, others | DONE, SEE PHOTOS
FLAE | D1 | EFFIGE dissemination within the joint event with the Dutch furniture delegation | Discussion about mutual state of the art regarding PEF methodology in the furniture sector and its further exploitation | 2019-12-12 | Dutch furniture representatives (VET center, Institutions, Companies, SMEs + Netherlands General Consulate in Milano) and furniture Italian representatives (VET center, Institutions, Companies, SMEs) | Done (Photos, presentation)
ENEA | D1 | Oral presentation | Training session | 2019-12-16 | personnel of Camere di Commercio lombarde | DONE, SEE PHOTOS
AGRICA | D1 | article in Italian |  | 2019-12-31 | companies, institutions, others
CAM | D1 | article in Italian |  | 2019-12-31 | companies, institutions, others
ENEA | D1 | Poster | SETAC Europe 30th Annual Meeting, 3-7 May 2020 (online Meeting) | 2020-05-31 | Academics, researchers | Abstract book
FLAE | D1 | EFFIGE dissemination during the Webinar Affichage environmental des produits textiles et de l’ameublement organized by EFIC | FLAE speech: EFFIGE project: effectiveness of the PEF methodology to evaluate the design projects, to better communicate the project sustainability features, to validate the “green claims | 2020-09-04 | 70 EU stakeholders for the Furniture and Textile sectors (Sectoral Association, Companies, Institution) | Done (Photos, presentation)
Camst | D1 | Press Conference - Bologna |  | 2020-11-01 | companies, institutions, others
Assofond | D1 | XXXV Foundry Congress (webinar) | presentation by Nicola Fabbri | 2020-11-12 | 250 people, foundries and stakholders | DONE
ENEA | D1 | Oral presentation | Webinar in the framework of the project Lombardia Circolare | 2020-11-24 | companies in Lombardia | done, see slides
ENEA | D1 | Oral presentation | IX Convegno Dell'Associazione Rete Italiana LCA | 9-11/12/20 | companies, academics, researchers | done, see slides
Assofond | D1 | The Made Green in Italy Certification (webinar) | presentation by Nicola Fabbri | 2020-12-16 | 15 people, assofond member companies | DONE
ENEA | D1 | Oral presentation | Webinar ABC "What kind of climate projects are undertaken by ABC’s partners? " | 2020-12-17 | companies, academics, researchers | done, see slides
ENEA | D1 | Articolo | SPECIALE -3/2019 ENEA magazine, I progetti ENEA per l' economia circolare | 2020-12-31 | all | DONE
ENEA | D1 | Articolo | SPECIALE -1/2020 ENEA magazine, I progetti ENEA per la sostenibilità agroalimentare | 2020-12-31 | all | DONE
AGRICA | D1 | article in Italian |  | 2020-12-31 | companies, institutions, others
CAM | D1 | article in Italian |  | 2020-12-31 | companies, institutions, others
Camst | D2 | article in English |  | 2020-12-31 | researchers
ENEA | D1 | Virtual meeting | Instituto Brasileiro de Informação em Ciência e Tecnologia- IBICT https://ibict.br/ | 2021-01-19 | researchers
ENEA | D1 | Lesson at schools | online didactics | 2021-02-26 | high school students, Istituto Tecnico Industriale Superiore Leonardo da Vinci - Carpi | DONE, SEE PHOTOS
ENEA | D1 | Lesson at schools | online didactics | 2021-03-04 | high school students, Istituto di Istruzione Superiore ETTORE MAJORANA - San Lazzaro di Savena | DONE, SEE PHOTOS
ENEA | D1 | radio program | Rubrica Prometeo in collaboration with CNR ( CHANNEL NEWS RADIO) Media: PEFStarter and Life Cycle Communication tool | 2021-03-07 | all | (https://www.adnkronos.com/rubrica-prometeo-del-7-marzo-realizzata-in-collaborazione-con-cnr-media_2rxa8RJ0qiS51qRnxONU4B?refresh_ce)
ENEA | D2 | Networking | Webinar about tools developed in EFFIGE: Medit and Database | 2021-03-15 | partners of LIFE MAGIS, LIFE TTGG and LIFE EFFIGE | DONE, see minutes
Assofond | D1 | Assofond steel foundries meeting (webinar) | presentation by Nicola Fabbri | 2021-03-24 | 15 people, assofond member companies | DONE
ENEA | D1 | Virtual meeting | Global Life Cycle Assessment Data Access network (GLAD) Metadata Working Group, presentation of Medit tool | 2021-04-07 | LCA database experts of UNEP Life Cycle Initiative | DONE
ENEA | D1 | Press release | Distribution to ENEAinform@ of information about PEFStarter and Life Cycle Communicaton tool | 2021-04-08 | national and international media, companies, public administrations, local bodies, associations and institutions | DONE , https://www.enea.it/it/Stampa/news/imprese-due-strumenti-innovativi-per-la-comunicazione-ambientale-di-prodotto
FLAE | D1 | Presentation of Effige and her tools to WG Circular Economy of EFIC | Presentation of EFFIGE experience with PEF and usefullness of EFFIGE Tools in communicating PEF Results | 2021-04-23 | 10 Representatives of European National furniture Associations | Done (Agenda, presentation)
Assofond | D1 | Assofond cast iron meeting | presentation by Nicola Fabbri | 2021-04-27 | 40 people, assofond member companies | DONE
FLAE | D1 | Webinar Strumenti per la Sostenibilità #1_Impronta ambientale di prodotto | EFFIGE Project Presentation and discussion about PEF methodology | 2021-04-27 | 60 Italian furniture stakeholders | Done (Photos, presentation)
ENEA | D2 | Virtual meeting | Webinar ""La Banca Dati Italiana LCA (BDI-LCA) come strumento per la circolarità nel settore delle costruzioni" " | 2021-04-28 | public administrations, academics, companies, trade associations and stakeholders of building sector | see screenshot
FLAE | D1 | FLA site web, EFFIGE news and progressive update | Dissemination action of the EFFIGE project with the publication of the news related to the project on the Linkedin communication channel | 2021-05-31 | Sector companies, associations, national media, researcher | DONE (FLA site)
Assofond | D1 | Effige final conference | press release | 2021-06-09 | national, local and specialized press | DONE
Assofond | D1 | Effige final conference | interview by GM Squaratti | 2021-06-09 | Adnkronos newswire | DONE
Assofond | D1 | Effige final conference | speech by Andrea Bianchi | 2021-06-09 | 300 people | DONE
ENEA | D1 | Conference | LIFE EFFIGE Final Conference | 2021-06-09 | companies, academics, researchers | see leaflet
ENEA | D1 | Virtual meeting | TRICK Project kickoff Meeting: presentation of PEFStarter | 2021-06-10 | companies, trade associations, researchers | done
ENEA | D1 | Interview | "GLAD Data Provider Requirements Survey" | 2021-06-16 | LCA database experts | draft minutes
ENEA | D1 | Virtual meeting | Tavolo Tecnico:Il ruolo della PA per l’integrazione della LCA nelle politiche di acquisto: dalla Banca Dati nazionale LCA ai tool di valutazione” | 2021-06-17 | public administrations, GPP experts | agenda meeting
ENEA | D1 | Virtual meeting | Meeting working group ICESP- Italian Circular Economy Stakeholder Platform | 2021-06-22 | companies, researchers | agenda meeting
Assofond | D1 | Assofond steel foundries meeting (webinar) | presentation by Nicola Fabbri | 2021-06-24 | 12 people, assofond member companies | DONE
FLAE | D1 | Presentation of EFFIGE in the Radio Programme RADIO IMMAGINA https://immagina.eu/ (three times in June and July 2021) | Presentation of EFFIGE experience with PEF and usefullness of EFFIGE Tools in communicating PEF Results | 2021-06-29 | General Public | Done / Foreseen (audio file)
AGRICA | D1 | article in english |  | 2021-06-30 | companies, institutions, others
CAM | D1 | article in english |  | 2021-06-30 | companies, institutions, others
Assofond | D1 | Article on "In Fonderia" magazine about Effige and Made Green in Italy | specialized magazine, Assofond network | 2021-06-30 | companies, institutions, others | DONE
Assofond | D1 | Article on "In Fonderia" magazine about Effige marketing tools | specialized magazine, Assofond network | 2021-06-30 | companies, institutions, others | DONE
Camst | D1 | Public workshop a Seed and Chips THE LEADING FOOD INNOVATION SUMMIT IN THE WORLD _milan |  | not realized | companies, institutions, others